| Policy Committee – 10 September 2013 PERFORMANCE MONITORING REPORT - QUARTER 1 2013/2014 |  |
| --- | --- |

Report of the Corporate Head of Financial Management

Ward(s) affected: All

- Purpose of Report - To present the Council’s Performance Monitoring Report for Quarter 1 2013/2014 in accordance with arrangements set out in the Council’s Performance Management Framework.

- Recommendations - Members are recommended to note and comment on progress and outcomes achieved.

- Council Plan Implementation Progress

  - Actions

Monitoring against the Council Plan show that good progress has been made on implementation of Council Plan actions.  22 of the 27 have been assessed as on target by those completing the updates. Two are due to start later and three have been classified as amber. Statuses are determined by comparing progress against previously agreed milestones.

| Priority | Action Status |
| --- | --- |
|  | Red | Amber | Green | Grey |
|  | all due elements of project are behind schedule / or not started | some due elements of project are behind schedule | on target as per project plan milestones | not yet started – not yet required |
| Affordable Housing |  |  | 1 |  |
| Enterprising Craven |  |  | 11 | 2 |
| Working with Communities |  |  | 3 |  |
| Greener Craven |  | 2 | 4 |  |
| Financial Resilience |  | 1 | 3 |  |
| Total | 0 | 3 (12%) (Progress summaries are shown overleaf) | 22 (88%) | 2 (Excluded from percentage calculation) |

| Council Plan Actions showing amber status |
| --- |
| Priority | Action | Progress | Status |
| Greener Craven -Work to reduce CO2 emissions from Council operations and from the Craven District as a whole | CP 13/17/18 - Implement the Climate Change Strategy and Action Plan 2013 - 2016 | Revised Climate Change Strategy being developed and will be presented to Policy Committee in September 2013 for approval. However, some actions are also being progressed against the 2013 targets to contribute towards CO2 reductions. | Amber |
| Greener Craven - Work to reduce waste and increase recycling levels within the District | CP 13/17/23 - Promote the Council's commercial recycling scheme | The number of commercial recycling accounts has increased from 180 to 219 over the period April 2013 to July 2013. | Amber |
| Financial Resilience - Implement major projects in the Asset Management Plan to support the achievement of value for money | CP 13/17/27 - Complete an options appraisal on Skipton Waste Management Depot and determine the preferred option for its future location | All options have been identified with four options being worked on in detail. Options appraisal is progressing well and will be complete by the end of August. | Amber |

The two actions not yet started are

- Enterprising Craven - Facilitate the development of business and employment Sites - Develop land at Station Road, High Bentham

- Enterprising Craven - Facilitate the development of business and employment Sites - Implement a project in South Craven subject to needs identified in the final Local Development Plan.

Full updates against all actions are provided at Appendix A (Page 5).

  - Indicators

Nine indicators are attached to the Council Plan of which seven are scheduled for collection each quarter.

- One is on target (FM 10 - Whole Council - Forecasted net expenditure against budget)

- Data is not yet available for two (WM 11 – Waste Management - Percentage of household waste sent for reuse, recycling and composting and WM 14 – Waste Management - The number of commercial recycling contracts in place)

- Two indicators are below target –

- ED 15 - Number of businesses assisted to improve their performance (5 against an annual target of 105. This is due to work plans having been revised to enable a team member to work on the Skipton Town Hall business plan.

- SH 10 (NI 155) – Strategic Housing - Number of affordable homes delivered (0 against an annual target of 40 in line with the Council Plan)

- The remaining two indicators are viewed as context information and are shown to indicate the environment in which the Council is working.

- ED 11 - Percentage change in the number of unemployed when compared with the position 12 Months – no target set. The number of unemployed had fallen by 19% in the year to 30th June 2013 (558 persons).

- ED 16 - The number of new business formations - no target set. 108 new businesses were formed in the period (120 in the corresponding period last year, a reduction of 10%).

A summary showing all Council Plan Indicators is available at Appendix  B.

- Implications

4.1	Financial and Value for Money (vfm) Implications –  None arising directly from this report.

4.2	Legal Implications – None arising directly from this report.

4.3	Contribution to Council Priorities – The report summarises performance and achievements against the action and performance indicators relating to council’s priorities as contained within the Council Plan.

4.4	Risk Management – Risks associated with the Council Plan and achievement of priorities are identified and included in the Council Risk Register as appropriate.

4.5	Equality Impact Assessment

An Equality Impact Assessment is not required as the report does not include policy matters for decision with potential impact on equality groups.

4.6	Consultations with Others

- CLT

- Service Managers

4.7	Access to Information: Background Documents

- Performance Information contained within TEN the Council’s Performance Management System

- Council Plan

4.8	Author of the Report

Rebecca Steel,  Performance Management Officer

Tel: 01756 706215

rsteel@cravendc.gov.uk

Appendices

Appendix A – Detailed Information - Action Updates

Appendix B – Detailed Information - Council Plan Indicators

Appendix C – Additional Information - Benefits and Planning Indicators

Note: Members are invited to contact the author in advance of the meeting with any detailed queries or questions.

Appendix A – Detailed Information - Action Updates

2013/14 Quarter One Council Plan Action Updates with Red Status - None

2013/14 Quarter One Council Plan Action Updates with Amber Status - Three – details shown below

2013/14 Quarter One Council Plan Action Updates with Green Status - Twenty-two – details shown below

2013/14 Quarter One Council Plan Action Updates with Grey Status - Two – details shown below

Priority Action Key Milestones Status Responsible Officer Progress Upda-ted by Date Affordable Housing - Increase the provision of affordable housing CP 13/17/01 - Explore, develop and implement new approaches to provide at least 40 new affordable homes per annum On-going - work with the Local Government NY and York Housing Board to deliver the Development Opportunities within the NY Local Investment Plan 2011-21 On-going - work with landowners, planning policy (CDC/YDNP), RPs and developers to identify and allocate potential affordable housing investment sites Jun 2013 - Submit "Get Craven Building - Stimulating the Construction Industry" options report to Policy Committee Sep 2013 - Review milestones in light of approved "Get Craven Building…" recommendations. Green Planning, Regeneration and Strategic Housing The last 5 units of affordable housing have been completed at the Woodlands Extra Care Scheme, Skipton. Settle Extra Care Scheme is on site but is unlikely to deliver until the next financial year and Garrs End Lane, Grassington is also on site which will deliver a further 4 units of affordable housing. Currently awaiting the outcome of Yorkshire Housing, Progress Group and Home Housing's bid for Affordable Homes Guarantee Programme monies that should deliver 46 units of affordable housing. Work is on-going with landowners, planning policy, and developers to identify and allocate potential affordable housing investment sites. There are currently 54 unimplemented planning permissions. A "Stimulating the Construction Industry" Report (Get Craven Building) was considered by Members on the 21st May where it was agreed in principle to establish a Craven District Council (CDC) shared equity scheme that uses commuted sums and other potential funding sources to build new homes on CDC owned land. It was also agreed in principle that CDC to use funding opportunities to build houses for private rent on its own land. A further report is to be taken to Policy in September. WA 19/07/13 Enterprising Craven - Address the impact of the recession CP 13/17/02 - Provide business support and advice services Aug 2013 - Programme of "bite sized" business events finalised Sep 2013 - Survey of businesses on Snaygill Industrial Estate and Airedale Business Centre completed Nov 2013 - Second Superfast North Yorkshire Business Breakfast Briefing held in Craven Mar 2014 - Formation of circles as part of the Full Circle Craven completed Mar 2014 - 20 businesses to have received support through the Online Retail Business Growth Programme Green Planning, Regeneration and Strategic Housing The Superfast North Yorkshire Business Support Programme has supported 57 businesses in the District; the support received includes one-to-one advice, workshops and a one-off grant. The four projects selected by the Council to receive funding from the New Homes Bonus reserve to deliver activities aimed at helping local businesses are underway. The following is a quick update on each project: Full Circle - the first information session has taken place with 8 businesses; this has resulted in the potential for the first circle to be created. Craven Connects - a survey of the 98 businesses on Snaygill Industrial Estate and Airedale Business Centre has been carried out, identifying the key issues and opportunities; this information will be used to inform where action is needed. Online Retail Business Growth Programme - 13 retail businesses have been selected to receive individual consultancy with personalised action plan. The businesses come from Settle, Crosshills, Kettlewell, Carleton, Skipton, Ingleton and Grassington. Building a Better Bentham - three workshops have been hosted, 5 members have received one-to-one mentoring, 3 new retail businesses have been set up, members of We Are Bentham have increased from 38 to 48, Facebook used to promote businesses. SES 18/07/13 Enterprising Craven - Address the impact of the recession CP 13/17/03 - Improve the economic vitality of market towns and villages across Craven Aug 2013 - Devise a solution to direct pedestrian traffic to Skipton town centre via Water Street Sep 2013 - New white on brown signs installed at the main entry points to Settle from the A65 Nov 2013 - Programme of improvements to High Bentham town centre agreed Jan 2014 - Signage scheme for Ingleton Industrial Estate agreed Green Planning, Regeneration and Strategic Housing At the request of businesses on Water Street in Skipton, a proposal to install new signs by the entrances from Coach Street has been agreed. Quotes have been invited for the supply of the signs; the aim is to have the signage in place by August. After consultation with Settle Town Council and Chamber of Trade, the design and costs for new white on brown signs on the A65 for Settle have been agreed with North Yorkshire County Highways. The order is due to be issued in July. The purpose of the work is to improve the appearance of the approaches to the town. A scheme to install coherent pedestrian signage for Bentham Town Centre has been agreed. An application for funding from the Yorkshire Dales LEADER programme has been approved - the value of the funding is 75% of total costs up to a maximum of £18,075. The project is designed to address a key issue identified by the community SES 18/07/13 Enterprising Craven - Address the impact of the recession CP 13/17/04 - Work with Welcome to Yorkshire and other partners to maximise the benefit of the Tour De France Grand Depart Yorkshire 2014 to Craven's economy May 2013 - Report to Policy Committee Nov 2013 - Legacy plan for Craven approved Future milestones to be agreed subject to the above and formation of the regional Working Groups for Tourism and Culture Green Planning, Regeneration and Strategic Housing Council Steering Group now in operation made up of Officers attending project groups organised by Welcome to Yorkshire. Arts/Culture workshop planned in September for Community groups to get involved with Cultural Festival. Workshops planned for Autumn to help businesses make the most of the Tour by either supplying services or making use of the increased focus in cycling. Project Team set up for delivery of Skipton Spectator Hub made up of Officers of CDC, Skipton town council and Skipton chamber of Trade - first planning meeting will be held in September. Have been engaging with Parish Council's to encourage them to formulate plans. No of fact sheets have been produced in conjunction with YDNPA and Richmondshire District Council. SH 17/07/13 Enterprising Craven - Determine future land allocations for housing and employment across the District outside the National Park CP 13/17/05 - Finalise and adopt the Local Development Plan (LDP) by the end of 2013 Jun 2013 - Consultation with parishes begins July 2013 - Consultation on employment land begins Nov 2013 - Draft Local Plan produced Mar 2014 - Draft Local Plan presented to Members Green Planning, Regeneration and Strategic Housing Informal parish consultation events have taken place with over 1,000 attendees. The information gathered is now being collated and analysed. A draft plan will then be compiled. Consultation on employment land has started ahead of schedule. DS 31/07/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/06 - Develop the South Skipton Employment Zone (incorporating Engine Shed Lane) Mar 2014 - Planning application for development of Wyvern Park received Green Planning, Regeneration and Strategic Housing The developer (Henry Boot Developments Ltd.) is continuing to progress their proposal to submit a planning application for a mixed employment development on the greenfield site. A public exhibition of the scheme was held in April 2013; discussions have taken place with statutory consultees such as the Environment Agency and North Yorkshire County Highways with regard to addressing constraints including flooding and access. Two agents have been appointed to market the site; it is reported that strong interest has been shown in the site. The project is on schedule to achieve the milestone. SES 16/07/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/07 - Develop land at Station Road, High Bentham Feb 2014 - Appraisal of options for providing access to the site Not started - not yet required Planning, Regeneration and Strategic Housing SES 09/07/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/08 - Support the development of the former Middle School buildings in Ingleton as a centre for small and start-up businesses Jan 2014 - Report to Policy Committee Green Planning, Regeneration and Strategic Housing The development of the former school buildings to provide affordable premises for rent to businesses is progressing. Operating as The i-Centre, two of the external buildings have been converted and leased to a bakery and marketing/design agency. A newly established business selling and erecting polytunnels has moved into the centre. Plans are underway to open a new gym - an enterprise being developed by two local young people. The project is on schedule to achieve the milestone. SES 16/07/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/09 - Work with the Threshfield Quarry Partnership to redevelop Threshfield Quarry Aug 2013 - Funding agreement signed Green Planning, Regeneration and Strategic Housing Application to Awards for All for funding to employ a Project Officer to develop a masterplan for the redevelopment of the Quarry was unsuccessful; the Trust are now looking at alternative sources of assistance. A number of projects are being progressed to support the development of the site for mixed use, including a bid to the Arts Council to prepare a business case for the creation an iconic sculpture. The Quarry has been registered as a potential film destination with Screen Yorkshire. A heritage trail has been developed; a leaflet is being produced; the site acts as a regular venue for artists' workshops. SES 18/07/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/10 - Implement a project in South Craven subject to needs identified in the final Local Development Plan Aug 2013 - Consult on employment land policy Additional milestones to be developed when LDP in place Not started - not yet required Planning, Regeneration and Strategic Housing DS 31/07/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/11 - Roll out broadband across Craven as a partner in the Superfast North Yorkshire project Jun 2013 - The Crossings Business Park and adjacent area enabled to receive fibre to the cabinet Sep 2013 - Snaygill Industrial Estate and Airedale Business Centre enabled to receive fibre to the cabinet Nov 2013 - Report to Policy Committee to consider arrangements for enabling additional fibre roll out Dec 2013 - High Bentham town centre enabled to receive fibre to the cabinet Green Planning, Regeneration and Strategic Housing The Superfast North Yorkshire project has fibre enabled 28 cabinets in the District, mainly in the Skipton and South Craven area. Further cabinets in Grassington, Settle, Bentham and Thornton-in-Craven are scheduled to be enabled during 2013. The cabinet serving Airedale Business Centre has been enabled following strong representation from the Council since it was omitted from the programme. As a result Airedale Business Centre and Snaygill Industrial Estate now have 100% coverage of superfast broadband. The Crossings Business Park has been partially connected to fibre broadband. An area of the Park will not receive a fibre to the cabinet service due to commercial issues. Alternative approaches are being investigated to ensure they receive equivalent speeds from a similar solution. SES 18/07/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/12 - Work with local communities to regenerate and revitalise the stretch of the Leeds Liverpool Canal Corridor within Craven, including the Southern Craven Greenways Scheme Aug 2013 - Access Development Plan completed Sep 2013 - Scope of the Phase 1 project confirmed Green Planning, Regeneration and Strategic Housing Access Development Plan for the Leeds to Liverpool Canal being developed. The purpose of the Plan is to devise a scheme for the development of a high quality greenway for walking and cycling between the current termination of the National Cycle Network near Riddleston to the border with Pendle District. The draft Plan has been used to support a funding bid to the Department of Transport Linking Communities - support for cycling in National Parks initiative. The bid (referred to as Connecting the Dales) was the subject of a report to Policy Committee in May 2013. Awaiting announcement by Government with regard to which bids have been successful SES 09/07/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/13 - Work with partners to deliver the Skipton Flood Alleviation Scheme Jun 2013 - Submit bid for financial assistance from the North Yorkshire LEP Growing Places Fund Nov 2013 - Commence works on site Green Planning, Regeneration and Strategic Housing Submission made to the North Yorkshire LEP Growing Places Fund for assistance to enable the scheme to commence this financial year and accelerate delivery of the economic benefits. The LEP Board has agreed in principle to an allocation from the Growing Places Fund pending a full appraisal of the business case. It is anticipated that the full business case will be completed for August 2013. A public information event was held in May 2013 as part of the pre-planning consultation. Feedback received will be used to help inform the preparation of the planning application, which it is expected, will be submitted in August 2013. SES 16/07/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/14 - Facilitate improved public transport into and throughout the District (e.g. Hellifield to Manchester line, Gargrave to Morecambe line) Aug 2013 - Hold stakeholder workshop Additional milestones depend on workshop outcomes Green Planning, Regeneration and Strategic Housing The stakeholder workshop was held ahead of schedule with representatives from parish councils along the rail line. Rail industry officers and the local M.P. attended. Prior to the event eight parish councils were visited to discuss the role of the Community Rail Partnership and station adoption possibilities. DS 31/07/13 Working with Communities - Support local citizens to become more actively involved in their communities CP 13/17/15 - Provide support for the development of Local Action Teams and facilitate the delivery of projects via the Localism Reserve Fund Sep 2013 - Review allocation method and priority areas for funding and submit to Policy Committee Jan 2014 - Evaluate demand and capacity for new projects and undertake publicity as appropriate Green IS, Comms and Projects Continue to support Friends of Aireville Park Group. Report taken to Policy Committee in July to give permission to apply to funding pots for work in certain areas of the park. The park masterplan which aligns the Council's plans for the park with the aspirations of FOAP will be taken to Policy Committee for Members to approve in September. Council Officers continue to attend monthly FOAP meeting and a meeting arranged with Skipton Members in August to go through draft Masterplan. Work has started on Community Grants/Core Funding Review to submit to Policy in September. SH 17/07/13 Working with Communities - Improve the opportunities available to residents of Greatwood and Horse Close, South Skipton CP 13/17/16 - Work with partners to fund a project worker to reduce deprivation and tackle long term unemployment, educational attainment and child poverty issues at Greatwood and Horse Close, South Skipton, identified as a key priority in the North Yorkshire Joint Strategic Needs Assessment Jul 2013 - Project structure and reporting streams agreed and in place Aug 2013 - Project worker on site By Mar 2014 - Funding bids made to continue projects Green IS, Comms and Projects Draft Project Plan in place, First meeting of Steering group to take place in September. Post has been advertised and interviews for Project Worker scheduled for 8th/9th August. SH 17/07/13 Working with Communities - Increase partner and community involvement in service delivery CP 13/17/17 - Explore and implement options for improved joint working with a range of partners including opportunities for community and voluntary sector organisations to deliver Council services May 2013 - 2 pilot group Green Dog Walkers set up Mar 2014 - Additional 3 groups in place Sep 2013 - Review options and establish future work plan Green IS, Comms and Projects Two pilot groups set up on Greatwood/Horseclose Estate and Glusburn and Cross Hills dog fouling group. Another group about to be set up in Airville Park via Friends of Aireville Park who are currently sourcing a sponsor for their materials. SH 17/07/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/18 - Implement the Climate Change Strategy and Action Plan 2013 - 2016 Jul 2013 - Strategy approval Approved actions to be completed in accordance with strategy/plan timescales Amber Assets and Projects Revised Climate Change Strategy being developed and will be presented to Policy Committee in September 2013 for approval. However, some actions are also being progressed against the 2013 targets to contribute towards CO2 reductions. HS 19/07/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/19 - Install energy efficient and renewable technologies to reduce the Council's carbon emissions Mar 2014 - Investigate potential technologies against payback & carbon emission reductions Jul 2013 - PV project entered delivery phase (subject to funding approval) Dec 2013 - PV project installation complete End march 2014 - carbon emission data collected for first quarter PV's in operation Green Assets and Projects Energy efficient technologies installed as part of the crematorium improvement project. Technologies being investigated for assets and improvement works including Skipton Town Hall, Skipton Depot and Whitefriars Toilets. PV project progressing with specification ready to tender. HS 19/07/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/20 - Conduct a minimum of five sustainability audits with Craven Businesses Sep 2013 - 2 audits complete Mar 2014 - 3 further audits complete Green Assets and Projects Working to identify businesses to undertake sustainability audits with. HS 19/07/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/21 - Facilitate group buying of utilities to support the community and reduce fuel poverty Sep 2013 - Campaign to promote the Community Switch Nov 2013 - Review the contract Green IS, Comms and Projects Following the initial auction held in April which was promoted with flyer in council Tax bills another auction was held on 4th June. To date 6% (9 people) of those who registered for April auction have actually made the switch. Registrations for the September auction will open in August. SH 17/07/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/22 - Promote Government energy efficiency incentives to Craven domestic and commercial properties Jun 2013 - replacement heating system to Book of Remembrance Chapel Jul 2013 - promotion of compost bins to householders Sep 2013 - upgraded lighting at Whitefriars PC's Mar 2014 - promotion of renewable technologies for businesses and residents Green Assets and Projects Heating system replaced in Book of Remembrance Chapel providing efficient heating system. Compost bins have been promoted to householders as part of the changes in garden waste collections. Lighting at Whitefriars PC's has been upgraded. HS 19/07/13 Greener Craven - Work to reduce waste and increase recycling levels within the District CP 13/17/23 - Promote the Council's commercial recycling scheme Apr 2013 - meet with the recyclate contractor to develop an appropriate action plan for commercial recycling waste streams Jul 2013 - review progress Amber Waste Management The number of commercial recycling accounts has increased from 180 to 219 over the period April 2013 to July 2013. PE 23/08/13 Financial Resilience - Ensure the Council's financial health remains robust CP 13/17/24 - Ensure the Council's Medium Term Financial Strategy (MT’S) is sustainable and responds to the Spending Review and Local Government Resource Review Sep 2013 - Review available Spending Review information Jan 2014 - Submit draft MT’S to CLT Feb 2014 - MT’S submitted to Policy Committee Green Financial Management Work has started on the preparation of the long term financial strategy which will provide the framework for the MT’S. The process of setting the 2014/15 budget is due to start and the MT’S will be updated to include three years detailed information and rolled forward accordingly. NC 01/08/13 Financial Resilience - Ensure the Council's financial health remains robust CP 13/17/25 - Ensure the Council is able to finance its requirements for capital investment Feb 2014 - Finance available for approved capital investments Green Financial Management As part of the approval of the 2013/14 Capital Programme the framework to ensure adequate capital resources are available for future years programme was developed. Sustainability of funding will also form part of the Council's long term financial strategy. NC 01/08/13 Financial Resilience - Ensure the Council's financial health remains robust CP 13/17/26 - Implement the Council's Value For Money Framework and Action Plan May 2013 - Review and update the VFM Framework and Action Plan for 2013/2014 Jun 2013 - CLT approval of revised document June Onwards - Ongoing implementation of revised action plan Green Financial Management The VFM Framework and Action Plan has been reviewed for 2013/2014 and approved by CLT. Revised actions have been integrated into Ten and implementation of the action plan is ongoing. CH 31/07/13 Financial Resilience - Implement major projects in the Asset Management Plan to support the achievement of value for money CP 13/17/27 - Complete an options appraisal on Skipton Waste Management Depot and determine the preferred option for its future location Apr 2013 - All options identified Jun 2013 - Options appraisals complete Sep 2013 - Member decision on option to implement Amber Assets and Projects All options have been identified with four options being worked on in detail. Options appraisal is progressing well and will be complete by the end of August. HS 19/07/13

Appendix B – Detailed Information – Council Plan Indicators

| Priority | Service | Ref. | Name | Collection Frequency | Actual 2012/13 | 2013/14 Target | Quarter One | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enterprising Craven | Economic Development | ED 11 | Percentage change in the number of unemployed when compared with the position 12 Months previously - Craven | Annually/Quarterly | New indicator for 2013/14 | Annual Target not set - context indicator | -19.1% |  |
|  |  | ED 14 | Vacant Retail Premises | Annually/Half-Yearly | 8.8% |  |  |  |
|  |  | ED 15 | Number of businesses assisted to improve their performance | Annually/Quarterly | 103 | Annual Target 105 | 5 |  |
|  |  | ED 16 | The number of new business formations | Annually/Quarterly | 436 | Context Indicator - no target set | 108 |  |
| Financial Resilience | Financial Management | FM 10 | Whole Council - Forecasted net expenditure against budget | Annually/Quarterly | New indicator for 2013/14 | Annual Target £6,369,180 (in line with budget book) | £6,323,473 |  |
|  |  | FM 12 | Level of general fund balances at financial year end | Annually | £1,030k |  |  |  |
| Affordable Housing | Strategic Housing | SH 10 (NI 155) | Number of affordable homes delivered | Annually/Quarterly | 29 | Annual Target 40 in line with Council Plan | 0 |  |
| Greener Craven | Waste Management | WM 11 | Percentage of household waste sent for reuse, recycling and composting | Annually/Quarterly | 48.67% yet to be verified | To be set once 12/13 outturn verified and garden waste scheme take-up established | Data/estimates not submitted |  |
|  |  | WM 14 | The number of commercial recycling contracts in place | Annually/Quarterly | New indicator for 2013/14 | Annual Target 216 | Data/estimates not submitted |  |

Appendix C – Additional Information - Benefits and Planning Indicators

| Full Name | Actual 2012/13 | Target 2013/14 | Q1 Target | Q1 Actual | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| PL 10 (NI 157a).Q - Processing of planning applications - Major Applications determined within statutory timescales (Q) | 40% based on old definition | Annual Target 40% (Local) | 40% | 100.00% |  |  |
| PL 11 (NI 157b).Q - Planning Applications: Minor applications (Q) | 70.28% | Annual Target 65% | 65% | 86.49% |  |  |
| PL 12 (NI 157c).Q - Planning Applications: 'Other' applications (Q) | 87.25% | Annual Target 80% | 80% | 95.65% |  |  |
| RB 10.Q - Housing Benefit and Council Tax Reduction - The number of claims in payment (Q) | 3498 at year end | Context Indicator - no target set |  | 3,696 |  |  |
| RB 11.Q - Housing Benefit and Council Tax Reduction - The average number of days to process changes in circumstances (Q) | 8.8 days | Annual Target 10 days | 14.5 | 9.0 |  | Quarterly targets were set to reflect changes in processing rates over the year and have been modelled on 2013/13 quarterly outturns |
| RB 12 (NI 181).Q - Housing Benefit and Council Tax Reduction - Time taken to process new claims and change events (Q) | 10.4 days | Annual Target 10.4 days | 14.1 | 10.7 |  |  |