| Policy Committee – 19 November 2013 PERFORMANCE MONITORING REPORT - QUARTER 2 2013/2014 |  |
| --- | --- |

Report of the Corporate Head of Financial Management

Ward(s) affected: All

- Purpose of Report - To present the Council’s Performance Monitoring Report for Quarter 2 2013/2014 in accordance with arrangements set out in the Council’s Performance Management Framework.

- Recommendations - Members are recommended to note and comment on progress and outcomes achieved.

- Council Plan Implementation Progress

  - Actions

Monitoring against the Council Plan show that good progress has been made on implementation of Council Plan actions.  17 of the 27 have been assessed as on target by those completing the updates. One is due to start later and nine have been classified as amber. Statuses are determined by comparing progress against previously agreed milestones.

| Priority | Action Status |
| --- | --- |
|  | Red | Amber | Green | Grey |
|  | all due elements of project are behind schedule / or not started | some due elements of project are behind schedule | on target as per project plan milestones | not yet started – not yet required |
| Affordable Housing |  |  | 1 |  |
| Enterprising Craven |  | 5 | 7 | 1 |
| Working with Communities |  |  | 3 |  |
| Greener Craven |  | 2 | 4 |  |
| Financial Resilience |  | 2 | 2 |  |
| Total | 0 | 9 (35%) (Progress summaries are shown overleaf) | 17 (65%) | 1 (Excluded from percentage calculation) |

| Priority | Action | Progress |
| --- | --- | --- |
| Enterprising Craven - Address the impact of the recession | CP 13/17/02 - Provide business support and advice services | Programme of business events has been drafted; comprising 15 events to run over the six-month period November to April 2014. The events cover a range of topics, including e-marketing, starting a business, how your business can benefit from welcoming cyclists, retailing in the 21st Century. The aim is to have the programme finalised by end of October. Delivery of the four projects awarded funding from the Council's New Homes Bonus reserve to is progressing. The following is a quick update on each project: Full Circle - work is underway with regard to the formation of a circle in Skipton - the Circle Formation Workshop is scheduled to take place in early October. Contact has been made with businesses interested in forming circles in Ingleton and South Craven. Craven Connects - a launch event is being organised for early October. To-date, a Business Snapshop survey has been conducted to identify collaboration opportunities; prepared and distributed a listing of all businesses on Snaygill Industrial Estate and Airedale Business Centre to enable resident businesses to start inter-trading; established baseline data. Online Retail Business Growth Programme - 10 retail businesses have received their individual consultancy visit and personalised action plan. Topics and dates for the masterclasses have been set. Building a Better Bentham - a total of four workshops have been hosted; the most recent dealing with employment law, a new leaflet promoting the services and goods available in the town centre has been produced, 5 members have received one-to-one mentoring, 3 new retail businesses have been set up, members of We Are Bentham have increased from 38 to 48, Facebook used to promote businesses. |
| Enterprising Craven - Address the impact of the recession | CP 13/17/03 - Improve the economic vitality of market towns and villages across Craven | Membership of South Craven Together, a group of local business owners, has increased from 7 to 22 businesses - approximately half of the businesses in the centre of Cross Hills. The group launched its first campaign to encourage residents to shop local; 23 businesses participated in the promotion and have reported an increase in trade. The group are discussing plans for a Christmas campaign. A scheme to consolidate signage around the vicinity of Weirside Gardens in Skipton has been agreed in consultation with businesses on Water Street and Coach Street. Procurement for the supply of new signs has been completed and are currently being manufactured. It is expected that physical completion of the Scheme will be achieved by November 2013. An order for the provision of new white on brown signs on the A65 for Settle has been issued to North Yorkshire County Highways. The purpose of the signs is to make passing traffic more aware of the facilities and services available in the town. Procurement for the supply and installation of a coherent pedestrian signage for Bentham Town Centre has been completed. Bentham Town Council has agreed to accept responsibility for the maintenance of the signage. Layouts for the signposts have been agreed; designs for the interpretation boards are being prepared. In accordance with the objective to add more colour and interest to Bentham Town Centre, the Town Team has used some of its Portas Town Team funding from Central Government to paint a mural on the interior of the refurbished Bus Shelter. The Team has also commissioned a local artist to do a series of paintings for blocked-up windows and doorways. Three proposals for the installation of a signage scheme for Ingleton Industrial Estate have been received. Consultation with the businesses on the Estate and North Yorkshire County Highways is being carried out before the contract to undertake the work is awarded. |
| Enterprising Craven - Determine future land allocations for housing and employment across the District outside the National Park | CP 13/17/05 - Finalise and adopt the Local Development Plan (LDP) by the end of 2013 | There have been 21 consultation events carried out in July 2013 involving communities from across Craven exploring the assumptions in the emerging Local Plan and also identifying from all of the sites that have been put forward for development, which would be preferable for development. The summaries from these events have been circulated to the relevant parish councils and the findings will be considered by the Craven Spatial Sub Committee in November. The viability study into housing and employment in Craven which forms the basis of any considerations regarding the introduction of a Community Infrastructure Levy has been completed. A presentation from the consultants to the CSSC has taken place. Bradley PC are the first to formally state that they intend to produce a Neighbourhood Plan which, if adopted, will become part of the local planning framework. |
| Enterprising Craven - Facilitate the development of business and employment Sites | CP 13/17/09 - Work with the Threshfield Quarry Partnership to redevelop Threshfield Quarry | The funding agreement for a contribution from this Council towards the costs of employing a Project Officer has been delayed. Following the unsuccessful application to the Awards for All for matched funding, the Threshfield Quarry Trustees are looking at alternative proposals for the creation of a masterplan to cover vision and scope of the project; identification of needs/benefits and potential partners; draft management structure; identification of funding opportunities and proposals for staged implementation. The Trustees have been awarded a grant from the Arts Council to prepare a business case for the creation an iconic sculpture. |
| Enterprising Craven - Improve infrastructure throughout the District | CP 13/17/12 - Work with local communities to regenerate and revitalise the stretch of the Leeds Liverpool Canal Corridor within Craven, including the Southern Craven Greenways Scheme | A first draft of the Access Development Plan is due to be received in October 2013. Members, together with the appropriate Parish Councils will be consulted on the draft document before the Plan is finalised. Once finalised, the Plan will be used to support future investment in the Canal Corridor. Unfortunately the bid to the Department for Transport (referred to as Connecting the Dales) was unsuccessful. The outcome of the bid highlighted the lack of a coherent plan for the future development of the Canal Corridor. Finalising the Access Development Plan will help the Council to evidence the need for investment in future funding bids. |
| Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole | CP 13/17/18 - Implement the Climate Change Strategy and Action Plan 2013 - 2016 | Following presentation of strategy to CLT, it was decided that the document should become a business plan and would not require approval of Policy Committee as it will be an operational business and action plan. The changes are currently being made to reflect the change. |
| Greener Craven - Work to reduce waste and increase recycling levels within the District | CP 13/17/23 - Promote the Council's commercial recycling scheme | Much progress has been made in promoting the service. The Council now has 214 Commercial recycling Customers (there were 180 in March 2013). |
| Financial Resilience - Ensure the Council's financial health remains robust | CP 13/17/26 - Implement the Council's Value For Money Framework and Action Plan | The VFM Framework and Action Plan has been reviewed for 2013/2014 and approved by CLT. Revised actions have been integrated into Ten and implementation of the action plan is ongoing. |
| Financial Resilience - Implement major projects in the Asset Management Plan to support the achievement of value for money | CP 13/17/27 - Complete an options appraisal on Skipton Waste Management Depot and determine the preferred option for its future location | Draft options appraisal presented to CLT in September. Further works required prior to finalisation and presentation to Policy Committee. |

The action not yet started is

- Enterprising Craven - Facilitate the development of business and employment Sites - Develop land at Station Road, High Bentham

Full updates against all actions are provided at Appendix A (Page 7).

  - Indicators

Nine indicators are attached to the Council Plan of which eight are scheduled for collection at the half year point.

- Two are on target (FM 10 - Whole Council - Forecasted net expenditure against budget and WM 14 - Waste Management - The number of commercial recycling contracts in place )

- Data is not yet available for two (WM 11 – Waste Management - Percentage of household waste sent for reuse, recycling and composting)

- Two indicators are below target –

- ED 15 - Number of businesses assisted to improve their performance (13 against an annual target of 105. This is due to work plans having been revised to enable a team member to work on the Skipton Town Hall business plan.

- SH 10 (NI 155) – Strategic Housing - Number of affordable homes delivered (5 against an annual target of 40 in line with the Council Plan)

- The remaining two indicators are viewed as context information and are shown to indicate the environment in which the Council is working.

- ED 11 - Percentage change in the number of unemployed when compared with the position 12 Months – no target set.

- ED 16 - The number of new business formations - no target set. 108 new businesses were formed in the period (120 in the corresponding period last year, a reduction of 10%).

A summary showing all Council Plan Indicators is available at Appendix  B.

- Implications

4.1	Financial and Value for Money (vfm) Implications –  None arising directly from this report.

4.2	Legal Implications – None arising directly from this report.

4.3	Contribution to Council Priorities – The report summarises performance and achievements against the action and performance indicators relating to council’s priorities as contained within the Council Plan.

4.4	Risk Management – Risks associated with the Council Plan and achievement of priorities are identified and included in the Council Risk Register as appropriate.

4.5	Equality Impact Assessment

An Equality Impact Assessment is not required as the report does not include policy matters for decision with potential impact on equality groups.

4.6	Consultations with Others

- CLT

- Service Managers

4.7	Access to Information: Background Documents

- Performance Information contained within TEN the Council’s Performance Management System

- Council Plan

4.8	Author of the Report

Rebecca Steel,  Performance Management Officer

Tel: 01756 706215

rsteel@cravendc.gov.uk

Appendices

Appendix A – Detailed Information - Action Updates

Appendix B – Detailed Information - Council Plan Indicators

Appendix C – Additional Information - Benefits and Planning Indicators

Note: Members are invited to contact the author in advance of the meeting with any detailed queries or questions.

Appendix A – Detailed Information - Action Updates

2013/14 Quarter Two Council Plan Action Updates with Red Status - None

2013/14 Quarter Two Council Plan Action Updates with Amber Status - Nine – details shown below

2013/14 Quarter Two Council Plan Action Updates with Green Status - Seventeen – details shown below

2013/14 Quarter Two Council Plan Action Updates with Grey Status - One – details shown below

Priority Action Key Milestones Status Responsible Officer Progress Updated by Date Affordable Housing - Increase the provision of affordable housing CP 13/17/01 - Explore, develop and implement new approaches to provide at least 40 new affordable homes per annum On-going - work with the Local Government NY and York Housing Board to deliver the Development Opportunities within the NY Local Investment Plan 2011-21 On-going - work with landowners, planning policy (CDC/YDNP), RPs and developers to identify and allocate potential affordable housing investment sites Jun 2013 - Submit "Get Craven Building - Stimulating the Construction Industry" options report to Policy Committee Sep 2013 - Review milestones in light of approved "Get Craven Building…" recommendations. Green Planning, Regeneration and Strategic Housing Disappointing quarter with no units of affordable housing delivered. Yorkshire Housing, Progress Housing Group and Home Housing Group have been successful in their bids to the Homes & Community Agency for Affordable Homes Guarantee Programme monies that will see the delivery 46 units of affordable housing. Start on site for these dwellings will need to be made by March 2015. The Garrs End Lane site at Grassington will now deliver 4 units of affordable housing in December 2013 rather than March 2014. There are currently a total of 69 units of affordable housing on site. There is a current realistic 'pipeline' total of 186 affordable housing units - 82 Rural and 108 Urban. Of this total some will have planning permissions and funding in place whilst others have planning permissions but will be reliant on the 'market' for delivery. A "Stimulating the Construction Industry" Report (Get Craven Building) was considered by Members on the 21st May where it was agreed in principle to establish a Craven District Council (CDC) shared equity scheme that uses commuted sums and other potential funding sources to build new homes on CDC owned land. A further report is to be taken to Policy Committee in January 2014 after dialogue with another local authority who adopted such an initiative. WA 08/10/13 Enterprising Craven - Address the impact of the recession CP 13/17/02 - Provide business support and advice services Aug 2013 - Programme of "bite sized" business events finalised Sep 2013 - Survey of businesses on Snaygill Industrial Estate and Airedale Business Centre completed Nov 2013 - Second Superfast North Yorkshire Business Breakfast Briefing held in Craven Mar 2014 - Formation of circles as part of the Full Circle Craven completed Mar 2014 - 20 businesses to have received support through the Online Retail Business Growth Programme Amber Planning, Regeneration and Strategic Housing Programme of business events has been drafted; comprising 15 events to run over the six-month period November to April 2014. The events cover a range of topics, including e-marketing, starting a business, how your business can benefit from welcoming cyclists, retailing in the 21st Century. The aim is to have the programme finalised by end of October. Delivery of the four projects awarded funding from the Council's New Homes Bonus reserve to is progressing. The following is a quick update on each project: Full Circle - work is underway with regard to the formation of a circle in Skipton - the Circle Formation Workshop is scheduled to take place in early October. Contact has been made with businesses interested in forming circles in Ingleton and South Craven. Craven Connects - a launch event is being organised for early October. To-date, a Business Snapshop survey has been conducted to identify collaboration opportunities; prepared and distributed a listing of all businesses on Snaygill Industrial Estate and Airedale Business Centre to enable resident businesses to start inter-trading; established baseline data. Online Retail Business Growth Programme - 10 retail businesses have received their individual consultancy visit and personalised action plan. Topics and dates for the masterclasses have been set. Building a Better Bentham - a total of four workshops have been hosted; the most recent dealing with employment law, a new leaflet promoting the services and goods available in the town centre has been produced, 5 members have received one-to-one mentoring, 3 new retail businesses have been set up, members of We Are Bentham have increased from 38 to 48, Facebook used to promote businesses. SS 09/10/13 Enterprising Craven - Address the impact of the recession CP 13/17/03 - Improve the economic vitality of market towns and villages across Craven Aug 2013 - Devise a solution to direct pedestrian traffic to Skipton town centre via Water Street Sep 2013 - New white on brown signs installed at the main entry points to Settle from the A65 Nov 2013 - Programme of improvements to High Bentham town centre agreed Jan 2014 - Signage scheme for Ingleton Industrial Estate agreed Amber Planning, Regeneration and Strategic Housing Membership of South Craven Together, a group of local business owners, has increased from 7 to 22 businesses - approximately half of the businesses in the centre of Cross Hills. The group launched its first campaign to encourage residents to shop local; 23 businesses participated in the promotion and have reported an increase in trade. The group are discussing plans for a Christmas campaign. A scheme to consolidate signage around the vicinity of Weirside Gardens in Skipton has been agreed in consultation with businesses on Water Street and Coach Street. Procurement for the supply of new signs has been completed and are currently being manufactured. It is expected that physical completion of the Scheme will be achieved by November 2013. An order for the provision of new white on brown signs on the A65 for Settle has been issued to North Yorkshire County Highways. The purpose of the signs is to make passing traffic more aware of the facilities and services available in the town. Procurement for the supply and installation of a coherent pedestrian signage for Bentham Town Centre has been completed. Bentham Town Council has agreed to accept responsibility for the maintenance of the signage. Layouts for the signposts have been agreed; designs for the interpretation boards are being prepared. In accordance with the objective to add more colour and interest to Bentham Town Centre, the Town Team has used some of its Portas Town Team funding from Central Government to paint a mural on the interior of the refurbished Bus Shelter. The Team has also commissioned a local artist to do a series of paintings for blocked-up windows and doorways. Three proposals for the installation of a signage scheme for Ingleton Industrial Estate have been received. Consultation with the businesses on the Estate and North Yorkshire County Highways is being carried out before the contract to undertake the work is awarded. SS 09/10/13 Enterprising Craven - Address the impact of the recession CP 13/17/04 - Work with Welcome to Yorkshire and other partners to maximise the benefit of the Tour De France Grand Depart Yorkshire 2014 to Craven's economy May 2013 - Report to Policy Committee Nov 2013 - Legacy plan for Craven approved Future milestones to be agreed subject to the above and formation of the regional Working Groups for Tourism and Culture Green Planning, Regeneration and Strategic Housing Council Steering Group now in operation made up of Officers attending project groups organised by Welcome to Yorkshire. Arts/Culture workshop held in September for Community groups to get involved with Cultural Festival and 45 people attended. Workshops planned for to help businesses make the most of the Tour by either supplying services or making use of the increased focus in cycling. First in Skipton is planned for 20th November 2013, with a second in Settle on 22nd January 2014. Skipton Project Team set up for delivery of Skipton Spectator Hub made up of Officers of CDC, Skipton Town council and Skipton chamber of Trade - furst planning meeting held. Will be screen/stage on High Street and second screen on Canal Basin which will also retain for the Sunday. Have been engaging with Parish Council's to encourage them to formulate plans and all Parish Councils on/near the route have been mailed and asked to nominate a Tour de France link. No of fact sheets have been produced in conjunction with YDNPA and Richmondshire District Council. First Tour de France Newsletter will be published following official route annoucement on 23rd October. Please note Legacy Report will now got to January Policy Committee. SH 8/10/13 Enterprising Craven - Determine future land allocations for housing and employment across the District outside the National Park CP 13/17/05 - Finalise and adopt the Local Development Plan (LDP) by the end of 2013 Jun 2013 - Consultation with parishes begins July 2013 - Consultation on employment land begins Nov 2013 - Draft Local Plan produced Mar 2014 - Draft Local Plan presented to Members Amber Planning, Regeneration and Strategic Housing There have been 21 consultation events carried out in July 2013 involving communities from across Craven exploring the assumptions in the emerging Local Plan and also identifying from all of the sites that have been put forward for development, which would be preferable for development. The summaries from these events have been circulated to the relevant parish councils and the findings will be considered by the Craven Spatial Sub Committee in November. The viability study into housing and employment in Craven which forms the basis of any considerations regarding the introduction of a Community Infrastructure Levy has been completed. A presentation from the consultants to the CSSC has taken place. Bradley PC are the first to formally state that they intend to produce a Neighbourhood Plan which, if adopted, will become part of the local planning framework. DS 17/10/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/06 - Develop the South Skipton Employment Zone (incorporating Engine Shed Lane) Mar 2014 - Planning application for development of Wyvern Park received Green Planning, Regeneration and Strategic Housing The developer (Henry Boot Developments Ltd.) is continuing to progress their proposal to submit a planning application for a mixed employment development on the greenfield site - an indicative date of November 2013 has been given for submission. The developer has reported that there is strong interest in the site, with agreements to provide in excess of 100,000 square feet of workspace for general industry and office accommodation in place. The economic impact assessment being prepared as part of the planning application estimates that the site will support in the region of 2,000 jobs. SS 08/10/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/07 - Develop land at Station Road, High Bentham Feb 2014 - Appraisal of options for providing access to the site Not started - not yet required Planning, Regeneration and Strategic Housing SS 08/10/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/08 - Support the development of the former Middle School buildings in Ingleton as a centre for small and start-up businesses Jan 2014 - Report to Policy Committee Green Planning, Regeneration and Strategic Housing The development of the former school buildings to provide affordable premises for rent to businesses is underway. A business plan is being prepared, which will form part of the proposed report to Policy Committee in January 2014. Operating as the i-Centre, the building is currently accommodating six businesses, with a further two businesses making use of the "hot desking" facilities. SS 08/10/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/09 - Work with the Threshfield Quarry Partnership to redevelop Threshfield Quarry Aug 2013 - Funding agreement signed Amber Planning, Regeneration and Strategic Housing The funding agreement for a contribution from this Council towards the costs of employing a Project Officer has been delayed. Following the unsuccessful application to the Awards for All for matched funding, the Threshfield Quarry Trustees are looking at alternative proposals for the creation of a masterplan to cover vision and scope of the project; identification of needs/benefits and potential partners; draft management structure; identification of funding opportunities and proposals for staged implementation. The Trustees have been awarded a grant from the Arts Council to prepare a business case for the creation an iconic sculpture. SS 08/10/13 Enterprising Craven - Facilitate the development of business and employment Sites CP 13/17/10 - Implement a project in South Craven subject to needs identified in the final Local Development Plan Aug 2013 - Consult on employment land policy Additional milestones to be developed when LDP in place Green Planning, Regeneration and Strategic Housing Initial consultation on employment land policy has taken place . Two additional rounds are scheduled for later in the process. DS 11/11/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/11 - Roll out broadband across Craven as a partner in the Superfast North Yorkshire project Jun 2013 - The Crossings Business Park and adjacent area enabled to receive fibre to the cabinet Sep 2013 - Snaygill Industrial Estate and Airedale Business Centre enabled to receive fibre to the cabinet Nov 2013 - Report to Policy Committee to consider arrangements for enabling additional fibre roll out Dec 2013 - High Bentham town centre enabled to receive fibre to the cabinet Green Planning, Regeneration and Strategic Housing There have been no new cabinets enabled in the District during Quarter 2, although work to improve the network infrastructure has taken place. It is expected that the Thornton-in-Craven cabinet will be enabled during Quarter 3 followed by cabinets in Bentham, Settle and Grassington. Detailed mapping of the areas to be enabled through the project can now be viewed on the website www.superfastnorthyorkshire.com The Chairman and Leader of the Council attended an opening event held at Principle Healthcare on Airedale Business Centre in Skipton at the end of September 2013 to promote the availability of superfast broadband on Airedale and Snaygill business parks. SS 08/10/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/12 - Work with local communities to regenerate and revitalise the stretch of the Leeds Liverpool Canal Corridor within Craven, including the Southern Craven Greenways Scheme Aug 2013 - Access Development Plan completed Sep 2013 - Scope of the Phase 1 project confirmed Amber Planning, Regeneration and Strategic Housing A first draft of the Access Development Plan is due to be received in October 2013. Members, together with the appropriate Parish Councils will be consulted on the draft document before the Plan is finalised. Once finalised, the Plan will be used to support future investment in the Canal Corridor. Unfortunately the bid to the Department for Transport (referred to as Connecting the Dales) was unsuccessful. The outcome of the bid highlighted the lack of a coherent plan for the future development of the Canal Corridor. Finalising the Access Development Plan will help the Council to evidence the need for investment in future funding bids. SES 08/10/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/13 - Work with partners to deliver the Skipton Flood Alleviation Scheme Jun 2013 - Submit bid for financial assistance from the North Yorkshire LEP Growing Places Fund Nov 2013 - Commence works on site Green Planning, Regeneration and Strategic Housing Application to the North Yorkshire LEP Growing Places Fund is being appraised, including due diligence checks. The Environment Agency is continuing to progress negotiations with landowners, preparation of designs and plans. It is anticipated that work on constructing the scheme will now start early next year. SS 08/10/13 Enterprising Craven - Improve infrastructure throughout the District CP 13/17/14 - Facilitate improved public transport into and throughout the District (e.g. Hellifield to Manchester line, Gargrave to Morecambe line) Aug 2013 - Hold stakeholder workshop Additional milestones depend on workshop outcomes Green Planning, Regeneration and Strategic Housing The stakeholder workshop was held ahead of schedule with representatives from parish councils along the rail line. Rail industry officers and the local M.P. attended. Prior to the event eight parish councils were visited to discuss the role of the Community Rail Partnership and station adoption possibilities. Meeting notes have now been circulated and a presentation will be made to the Local Rail Partnership on key findings and next steps. Additional milestones will then be agreed for the remainder of this financial year. DS 22/10/13 Working with Communities - Support local citizens to become more actively involved in their communities CP 13/17/15 - Provide support for the development of Local Action Teams and facilitate the delivery of projects via the Localism Reserve Fund Sep 2013 - Review allocation method and priority areas for funding and submit to Policy Committee Jan 2014 - Evaluate demand amd capacity for new projects and undertake publicity as appropriate Green IS, Comms and Projects Continue to support Friends of Aireville Park Group. Report taken to Policy Committee in July to give permission to apply to funding pots for work in certain areas of the park. The park materplan which aligns the Council's plans for the park with the aspirations of FOAP was approved by Policy Committee in September. Council Officers continue to attend monthly FOAP meeting and a meeting held with Skipton Members in August to go through draft Masterplan. Community Grants/Core Funding Review report completed but not taken to Policy in September as Members want to consider grants/core funding at their next away day in Oct/Nov SH 8/10/13 Working with Communities - Improve the opportunities available to residents of Greatwood and Horse Close, South Skipton CP 13/17/16 - Work with partners to fund a project worker to reduce deprivation and tackle long term unemployment, educational attainment and child poverty issues at Greatwood and Horse Close, South Skipton, identified as a key priority in the North Yorkshire Joint Strategic Needs Assessment Jul 2013 - Project structure and reporting streams agreed and in place Aug 2013 - Project worker on site By Mar 2014 - Funding bids made to continue projects Green IS, Comms and Projects Draft Project Plan in place agreed in principle and final amendments now being made. Project Plan will be signed off by end of October. First meeting of Steering group took place in September. Project worker Gemma Basham in post in September and Community engagement schedule is being worked up. Meeting with Director of Public Health for North Yorkshire, Dr Lincoln Sargeant re possible funding for the project. SH 8/10/13 Working with Communities - Increase partner and community involvement in service delivery CP 13/17/17 - Explore and implement options for improved joint working with a range of partners including opportunities for community and voluntary sector organisations to deliver Council services May 2013 - 2 pilot group Green Dog Walkers set up Mar 2014 - Additional 3 grpups in place Sep 2013 - Review options and establish future work plan Green IS, Comms and Projects Two pilot groups set up on Greatwood/Horseclose Estate and Glusburn and Cross Hills dog fouling group. Another group about to be set up in Aireville Park via Friends of Aireville Park who are currently sourcing a sponsor for their materials. SH 08/10/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/18 - Implement the Climate Change Strategy and Action Plan 2013 - 2016 Jul 2013 - Strategy approval Approved actions to be completed in accordance with strategy/plan timescales Amber Assets and Projects The Climate Change Business Plan is complete and Craven District Council has signed up to be a ‘Climate Local’ Council. HS 06/11/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/19 - Install energy efficient and renewable technologies to reduce the Council's carbon emissions Mar 2014 - Investigate potential technologies against payback & carbon emission reductions Jul 2013 - PV project entered delivery phase (subject to funding approval) Dec 2013 - PV project installation complete End march 2014 - carbon emission data collected for first quarter PV's in operation Green Assets and Projects Energy efficient technologies installed as part of the crematorium improvement project. Technologies being investigated for assets and impovement works including Skipton Town Hall, Skipton Depot and Whitefriars Toilets. PV project progressing well with contractor procured and installation due to complete by the end of December 2013. HS 01/10/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/20 - Conduct a minimum of five sustainability audits with Craven Businesses Sep 2013 - 2 audits complete Mar 2014 - 3 further audits complete Green Assets and Projects Two sustainability audits were completed by the end of September in line with agreed milestones. HS 21/10/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/21 - Facilitate group buying of utilities to support the community and reduce fuel poverty Sep 2013 - Campaign to promotty the Community Switch Nov 2013 - Review the contract Green IS, Comms and Projects Following the inital auction held in April which was promoted with flyer in council Tax bills another auction was held on 4th June. To date 6% (9 people) of those who registered for April auction have actually made the switch. A third auction closed on the19th October and was promoted on the Council website. Results are still awaited. SH 08/10/13 Greener Craven - Work to reduce CO2 emissions from Council operations and from the Craven District as a whole CP 13/17/22 - Promote Government energy efficiency incentives to Craven domestic and commercial properties Jun 2013 - replacement heating system to Book of Remembrance Chapel Jul 2013 - promotion of compost bins to householders Sep 2013 - upgraded lighting at Whitefriars PC's Mar 2014 - promotion of renewable technologies for businesses and residents Green Assets and Projects Heating system replaced in Book of Remembrance Chapel providing efficient heating system. Compost bins have been promoted to householders as part of the changes in garden waste collections. Lighting at Whitefriars PC's has been upgraded. HS 22/10/13 Greener Craven - Work to reduce waste and increase recycling levels within the District CP 13/17/23 - Promote the Council's commercial recycling scheme Apr 2013 - meet with the recyclate contractor to develop an appropriate action plan for commercial recycling waste streams Jul 2013 - review progress Amber Waste Management Much progress has been made in promoting the service. The Council now has 214 Commercial recycling Customers (there were 180 in March 2013). PE 07/10/13 Financial Resilience - Ensure the Council's financial health remains robust CP 13/17/24 - Ensure the Council's Medium Term Financial Strategy (MTFS) is sustainable and responds to the Spending Review and Local Government Resource Review Sep 2013 - Review available Spending Review information Jan 2014 - Submit draft MTFS to CLT Feb 2014 - MTFS submitted to Policy Committee Green Financial Management The process of setting the 2014/15 budget has commenced. This will be set in the context of a longer-term Financial Strategy. The MTFS will be updated to include three years detailed information and rolled forward accordingly. JM 15/10/13 Financial Resilience - Ensure the Council's financial health remains robust CP 13/17/25 - Ensure the Council is able to finance its requirements for capital investment Feb 2014 - Finance available for approved capital investments Green Financial Management As part of the approval of the 2013/14 Capital Programme the framework to ensure adequate capital resources are available for future years programme was developed. Sustainability of funding will also form part of the Council's longer term financial strategy. NC 14/10/13 Financial Resilience - Ensure the Council's financial health remains robust CP 13/17/26 - Implement the Council's Value For Money Framework and Action Plan May 2013 - Review and update the VFM Framework and Action Plan for 2013/2014 Jun 2013 - CLT approval of revised document June Onwards - Ongoing implementation of revised action plan Amber Financial Management The VFM Framework and Action Plan has been reviewed for 2013/2014 and approved by CLT. Revised actions have been integrated into Ten and implementation of the action plan is ongoing. CH 14/10/13 Financial Resilience - Implement major projects in the Asset Management Plan to support the achievement of value for money CP 13/17/27 - Complete an options appraisal on Skipton Waste Management Depot and determine the preferred option for its future location Apr 2013 - All options identified Jun 2013 - Options appraisals complete Sep 2013 - Member decision on option to implement Amber Assets and Projects Draft options appraisal presented to CLT in September. Further works required prior to finalisation and presentation to Policy Committee. HS 01/10/13

Appendix B – Detailed Information – Council Plan Indicators

| Priority | Service | Ref. | Name | Collection Frequency | Actual 2012/13 | 2013/14 Target | Half Year | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enterprising Craven | Economic Development | ED 11 | Percentage change in the number of unemployed when compared with the position 12 Months previously - Craven | Annually/Quarterly | New indicator for 2013/14 | Annual Target not set - context indicator | -30.4% | Half Year figure at end of August. Although no target has been set for this indicator the number of unemployed at the end of August had decreased by almost a third when compared to the level at the end of August 2012. |
|  |  | ED 14 | Vacant Retail Premises | Annually/Half-Yearly | 8.8% | Annual Target not set - context indicator | 10.1% |  |
|  |  | ED 15 | Number of businesses assisted to improve their performance | Annually/Quarterly | 103 | Annual Target 105 | 13 |  |
|  |  | ED 16 | The number of new business formations | Annually/Quarterly | 436 | Context Indicator - no target set | 170 |  |
| Financial Resilience | Financial Management | FM 10 | Whole Council - Forecasted net expenditure against budget | Annually/Quarterly | New indicator for 2013/14 | Annual Target £6,369,180 (in line with budget book) | £6,145,134 |  |
|  |  | FM 12 | Level of general fund balances at financial year end | Annually | £1,030k |  |  |  |
| Affordable Housing | Strategic Housing | SH 10 (NI 155) | Number of affordable homes delivered | Annually/Quarterly | 29 | Annual Target 40 in line with Council Plan | 5 |  |
| Greener Craven | Waste Management | WM 11 | Percentage of household waste sent for reuse, recycling and composting | Annually/Quarterly | 48.67% yet to be verified | To be set once 12/13 outturn verified and garden waste scheme take-up established | Data/estimates not submitted |  |
|  |  | WM 14 | The number of commercial recycling contracts in place | Annually/Quarterly | New indicator for 2013/14 | Annual Target 216 | 221 |  |

Appendix C – Additional Information - Benefits and Planning Indicators

| Full Name | Actual 2012/13 | Target 2013/14 | Half Year Target | Half Year Actual | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| PL 10 (NI 157a).Q - Processing of planning applications - Major Applications determined within statutory timescales (Q) | 40% based on old definition | Annual Target 40% (Local) | 40% | 100.00% |  |  |
| PL 11 (NI 157b).Q - Planning Applications: Minor applications (Q) | 70.28% | Annual Target 65% | 65% | 81.25% |  |  |
| PL 12 (NI 157c).Q - Planning Applications: 'Other' applications (Q) | 87.25% | Annual Target 80% | 80% | 92.31% |  |  |
| RB 10.Q - Housing Benefit and Council Tax Reduction - The number of claims in payment (Q) | 3498 at year end | Context Indicator - no target set |  | 3,518 |  |  |
| RB 11.Q - Housing Benefit and Council Tax Reduction - The average number of days to process changes in circumstances (Q) | 8.8 days | Annual Target 10 days | 13.1 | 9.4 |  | Quarterly targets were set to reflect changes in processing rates over the year and have been modelled on 2013/13 quarterly outturns |
| RB 12 (NI 181).Q - Housing Benefit and Council Tax Reduction - Time taken to process new claims and change events (Q) | 10.4 days | Annual Target 10.4 days | 13.1 | 10.3 |  |  |