APPENDIX A

CRAVEN DISTRICT COUNCIL

INTERNAL AUDIT 2013/14

| Annual Audits | Approved Plan | Actual April-Dec | Comments |
| --- | --- | --- | --- |
| Benefits | 2012/13 b/fd | 5 | 19 | Reported June 2013. “Significant”. |
|  | 2013/14 | 30 | 3 | Focus on welfare benefit changes. Audit in progress. |
| Procurement | (Contracts) | 10 | 11 | Contract Management reported in Jan 2014. “Significant”. |
| Treasury Management | 2012/13 b/fd 2013/14 | 3 5 | - - | Audit at draft report stage. |
| Council Tax/ NDR | 2012/13 b/fd 2013/14 | 5 20 | 19 4 | Reported in June 2013. “Good”. To focus on changes e.g NDR localisation. Audit in progress. |
| Payroll | 2012/13 b/fd 2013/14 | 2 15 | 17 3 | Reported June 2013. Finance “Good” HR “Partial”. Audit in progress. |
| Debtors | 2012/13 b/fd 2013/14 | 5 10 | 2 1 | Reported June 2013 “Good”. Audit in progress |
| Creditors | 2013/14 | 10 | - | 2012/13 - Reported Dec 2012. “Partial” 2013/14 – Audit in progress. |
|  |  | 120 | 79 |  |

| Risk Assessed Systems | Approved Plan | Actual April-Dec | Comments |
| --- | --- | --- | --- |
| BVS Service Charge | 15 | 7 | Completed. Reported Sept 2013. |
| Members Expenses | 5 | 9 | Completed. Reported Jan 2014 “Partial”. Report back in March. (See separate agenda item). |
| Trade Waste – (Processes and procedures) | 15 | 20 | Completed. Reported March 2014. (See separate agenda item). “Good” |
| Trade Waste – Strategic Review | - | 4 | Completed. Reported March 2014. “Good”. Report with Corporate Leadership Team. |
| Mechanics Workshop | 15 | 18 | Audit in progress. Carried forward to 2014/15. |
| Car Parking – Civil Enforcement | 10 | - | Audit deferred as Select Committee to undertake review (A&G decision Nov 2013). |
| Anti-Fraud Strategy | 10 | 8 | Completed. Reported Jan 2014. |
| Craven Pool – 2012/13 c/fd | 5 | 6 | Completed. Reported Sept 2013 “Partial”. Update on implementation of recommendations reported March 2014. (See separate item on agenda) |
| Museum/Gallery and TIC (Town Hall processes and procedures) | - | - | Additional audit approved by A&G Nov 2013. Deferred to 2014/15 due to other priorities. |
|  | 75 | 72 |  |

| IS | Approved Plan | Actual April-Dec | Comments |
| --- | --- | --- | --- |
| Overall Provision | 25 |  |  |
| Completing 2012/13 Audits Data Handling (Members) Service Desk |  | 2 9 | Completed. Reported in Sept 2013. “No”. Completed. Reported in Sept 2013 “Good”. |
| 2013/14 Audits Data Protection Payment Card Industry Data Standards |  | 16 17 | Draft report stage. Draft report stage. |
|  | 25 | 44 |  |
| Contingency | 11 | - | Re-allocated to Audits. |

| Other Work | Approved Plan | Actual April-Dec | Comments |
| --- | --- | --- | --- |
| Planning/Management | 14 | 19 | Time spent by Audit Manager and Principal Auditor on audit planning and reviewing audit reports. |
| Audit Committee Papers | 5 | 5 | Time spent on producing Committee reports and attendance at meetings. |
|  | 19 | 24 |  |
| TOTAL | 250 | 219 |  |