| AUDIT AND GOVERNANCE COMMITTEE – 24 March 2014 Internal Audit Plan 2013/14 Progress Report |  |
| --- | --- |

Report of the Audit Manager – Shared Internal Audit Service

Ward(s) affected: All

1.0	PURPOSE OF REPORT

1.1	This is to update Committee Members about the progress made on the 2013/14 Internal Audit Plan.

2.0	RECOMMENDATION

Members are recommended to:-

2.1	Note the contents of the report and the attached Appendix.

3.0	BACKGROUND

3.1	At its meeting on 24 June 2013, the Audit and Governance Committee approved the Internal Audit Plan for 2013/14. The attached Appendix sets out the days allocated to the various audits and the days spent during the period April-December 2013, the latest date for which comprehensive time recording information is available. The Appendix also includes an up to date commentary as at the time of writing.

3.2	At its meeting on 11 November 2013, the Committee resolved to replace the audit of Civil Parking Enforcement included in the original Audit Plan with a review of the income collection and banking arrangements at the Museum, Gallery and Tourist Information Centre.

3.3	In the Annual Audits, the majority of the time spent during April-December was on completing audits from 2012/13 on the major financial systems (57 days out of the total of 79). As explained previously these audits are timetabled for late Q3/Q4 which means that there can be a carry-over into the following year. As can be seen from the Appendix, the relevant reports were submitted to the Audit and Governance Committee in June. The 2013/14 audits are now well in hand. It is currently anticipated that these will be completed by early April.

3.4	The Annual Audits also includes work on Procurement/Contracts. This is now completed for 2013/14 and was reported to the Committee in January.

3.5	Particular points to note on the ‘Risk Assessed Systems” include:-

- Member Expenses. The original report was submitted to the Committee in January with a “Partial” level of assurance that adequate and effective controls are in place and working. As requested, there is a follow-up report on this agenda on the implementation of specific recommendations which were considered to be relatively urgent.

- Trade Waste – This work is now completed. There are two reports attached to the agenda for this meeting – the first on processes and procedures (mainly financial) and the second which is a strategic review.

- Craven Pool – The original report was submitted to the Committee in September with a “Partial” level of assurance. There is a follow-up report from Internal Audit to this meeting of the Committee.

- Museum, Gallery and TIC – It has not been possible to start this audit in 2013/14 as originally anticipated due to other priorities. This audit has now been carried forward to 2014/15.

3.6	On IS Audits, 11 days were spent on completing the 2012/13 audits on the Service Desk and Data Sharing (Members). Both reports were submitted to the Committee in September. The 2013/14 audits on Data Protection and the Payment Card Industry Data Standards are at draft report stage.

3.7	Members will see from the Appendix that as at the end of December 219 days, of the total provision of 250 days, had been spent. It is therefore probable that by the end of March, actual time will be greater than the total provision. If this proves to be a reality, consideration will be given at the time on how to accommodate this within the Shared Service.

4.0	IMPLICATIONS

4.1	Financial and value for money – none.

4.2	Legal – none.

4.3	Contribution to Council priorities – Council transformation.

4.4	Risk Management – the internal audit function is an integral part of internal control.

4.5	Equality/Impact Assessment – not applicable.

5.0	CONSULTATION WITH OTHERS

5.1	Corporate Head (Financial Management andS151 Officer).

6.0	ACCESS TO INFORMATION BACKGROUND DOCUMENTS

6.1	None.

7.0	AUTHOR OF THE REPORT

Martin Helm, Audit Manager, Craven District Council and Harrogate Borough Council Shared Internal Audit Service.

Telephone:  	01423 556114

Email:		martin.helm@harrogate.gov.uk

Note:  Members are invited to contact the author in advance of the meeting with any detailed queries or questions.